## IfcBuildingElementProxy
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75eA | 2802362 | IfcBuildingElementProxy | 2802362 | FFL\IfcBuildingElementProxy\2802362__3osoug9Ev0g85atawY75eA\meta.json | Baseboard installation | Not Started | A total of 3 types of input information are considered in the assessment, while temporal context information is unavailable. The local images indicate that no skirting/baseboard is visible and exposed wall framing is observed. The point cloud summary shows low geometric correspondence between BIM and the as-built scan (coverage ≈ 0.33, voxel IoU ≈ 0.30). The BIM semantics describe the element as a wall skirting/baseboard finishing component. The temporal context shows no temporal history is available. Considering these 3 types of information together, the element is assessed as Not Completed. | Not Started | A total of 4 types of input information are considered in the assessment, and no information is missing. The local images indicate that no skirting/baseboard is visible along the wall, while the wall surface appears finished without exposed structural framing, suggesting that the wall has progressed to a later construction stage but the finishing trim has not yet been installed. The point cloud summary shows moderate geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.580, coverage hit ≈ 0.833, voxel recall ≈ 0.857, and voxel IoU ≈ 0.369, indicating that surrounding wall geometry is largely captured in the scan, but the specific skirting element defined in the BIM model is not clearly present. The BIM semantics describe the element as a wall skirting/baseboard finishing component, which is typically installed during the final interior finishing stage. The temporal context shows that the element was previously not started at the earlier time step (t-1). Considering these 4 types of information together, the element is assessed as Not Completed. | Uncertain | A total of 3 types of input information are considered in the assessment, while local image information is unavailable. The point cloud summary shows very low geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.083, coverage hit ≈ 0.073, voxel recall ≈ 0.107, and voxel IoU ≈ 0.086, indicating that only a very small portion of the expected BIM geometry is observed in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component. The temporal context shows that the element was previously not started at the earlier time step (t-1). Considering these 3 types of information together, the available evidence is insufficient to reliably determine the construction status of the element, and the result is assessed as Uncertain. | Uncertain | A total of 3 types of input information are considered in the assessment, while local image information is unavailable. The point cloud summary shows extremely low geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.033, coverage hit ≈ 0.027, voxel recall ≈ 0.036, and voxel IoU ≈ 0.030, indicating that almost none of the expected BIM geometry is observed in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component. The temporal context shows that the construction status remained uncertain at the previous time step (t-1). Considering these 3 types of information together, the available evidence is still insufficient to reliably determine the construction status of the element, and the result is assessed as Uncertain. | Uncertain | A total of 3 types of input information are considered in the assessment, while local image information is unavailable. The point cloud summary shows relatively high surface coverage and geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.763, coverage hit ≈ 0.773, voxel recall ≈ 0.750, and voxel IoU ≈ 0.328. These results suggest that a substantial portion of the expected BIM geometry is captured in the scanned data; however, without supporting visual evidence, it is not possible to confirm whether the detected geometry corresponds specifically to the skirting/baseboard element or to adjacent finished surfaces. The BIM semantics describe the element as a wall skirting/baseboard finishing component. The temporal context shows that the construction status remained uncertain at the previous time step (t-1). Considering these 3 types of information together, the available evidence is still insufficient to reliably determine the construction status of the element, and the result is assessed as Uncertain.
3osoug9Ev0g85atawY75e9 | 2802363 | IfcBuildingElementProxy | 2802363 | FFL\IfcBuildingElementProxy\2802363__3osoug9Ev0g85atawY75e9\meta.json | Baseboard installation | Not Started | A total of 3 types of input information are considered in the assessment, while temporal context information is unavailable because this is the first time step. The local images indicate that no skirting/baseboard is visible on either observed face of the wall where the BIM element is expected, suggesting that the element has not yet appeared in the as-built environment. The point cloud summary shows relatively high geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.759, coverage hit ≈ 0.767, voxel recall ≈ 0.758, and voxel IoU ≈ 0.321; however, since the local images confirm that the wall surfaces do not contain the expected attached component, the detected geometry is more likely associated with adjacent wall surfaces rather than the skirting element itself. The BIM semantics describe the element as a wall skirting/baseboard finishing component with an approximate rectangular section of 100 × 100 mm and a length of about 6.35 m, which is expected to be attached to the wall surface during the finishing stage. Considering these 3 types of information together, the element is assessed as Not Started | Not Started | A total of 4 types of input information are considered in the assessment, and no information is missing. The local images indicate that only one side of the wall was observed at this time step, and no skirting/baseboard is visible on the observed wall surface, which means the expected element is still not confirmed in the as-built environment. The point cloud summary shows moderate geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.431, coverage hit ≈ 0.512, voxel recall ≈ 0.545, and voxel IoU ≈ 0.346; however, because the visual evidence from the observed side does not show the attached wall component, the detected geometry may still correspond to adjacent wall surfaces rather than the skirting element itself. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Not Started. | Not Started | A total of 4 types of input information are considered in the assessment, and no information is missing. The local images indicate that only one side of the wall was observed at this time step, and no skirting/baseboard is visible on the observed wall surface, which means the expected element is still not confirmed in the as-built environment. The point cloud summary shows high surface coverage but weak voxel-level consistency between the BIM model and the as-built scan, with coverage ≈ 0.758, coverage hit ≈ 0.767, voxel recall ≈ 0.545, and voxel IoU ≈ 0.157; this suggests that although nearby wall geometry is substantially captured, the detected points do not provide strong evidence for the presence of the specific skirting/baseboard element. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Not Started. | Uncertain | A total of 4 types of input information are considered in the assessment, and no information is missing. The local images indicate that the viewing angle is highly oblique and does not clearly capture the target wall region where the skirting/baseboard element is expected, making it difficult to visually verify the presence or absence of the component. The point cloud summary shows very low geometric correspondence between the BIM model and the as-built scan, with coverage ≈ 0.043, coverage hit ≈ 0.028, voxel recall ≈ 0.030, and voxel IoU ≈ 0.026, indicating that almost none of the expected BIM geometry is detected in the scanned data; however, this may also result from incomplete scanning coverage rather than the true absence of the element. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the available evidence is insufficient to reliably determine the construction status of the element, and the result is assessed as Uncertain | Uncertain | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that only one side of the wall was observed, no skirting/baseboard is visible on the observed side, and the lighting condition is poor, making visual verification unreliable. The point cloud summary shows moderate geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.484, coverage hit ≈ 0.556, voxel recall ≈ 0.576, voxel IoU ≈ 0.358). The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Uncertain at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Uncertain.
3osoug9Ev0g85atawY75e8 | 2802364 | IfcBuildingElementProxy | 2802364 | FFL\IfcBuildingElementProxy\2802364__3osoug9Ev0g85atawY75e8\meta.json | Baseboard installation | Not Started | A total of 3 types of input information are considered in the assessment, while temporal context information is not available. The local images indicate that only one side of the wall is visible in the available images, and no skirting/baseboard is observed on the visible side; instead, exposed steel framing of the wall structure is present, suggesting that the wall finishing stage has not yet been reached. The point cloud summary shows very low geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.146, coverage hit ≈ 0.143, voxel recall ≈ 0.100, voxel IoU ≈ 0.059), indicating that the expected BIM geometry is largely absent in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. Considering these 3 types of information together, the element is assessed as Not Started. | Not Started | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that only one side of the wall is observed, no skirting/baseboard is visible on the observed side, and the wall structure remains exposed, suggesting that the wall finishing stage has not yet been reached. The point cloud summary shows very low geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.063, coverage hit ≈ 0.082, voxel recall ≈ 0.100, voxel IoU ≈ 0.080). The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Not Started. | Uncertain | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that only one side of the wall is observed and no skirting/baseboard is visible on the observed side, although the wall surface appears finished and plastered. The point cloud summary shows high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.905, coverage hit ≈ 0.909, voxel recall ≈ 0.900, voxel IoU ≈ 0.290), suggesting that surrounding wall geometry is well captured in the scan. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the available evidence is insufficient to confirm the presence of the skirting element, and the element is assessed as Uncertain. | Completed | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that only one side of the wall is observed and a skirting/baseboard-like structure appears to be present on the wall surface, although the lighting condition is relatively dark. The point cloud summary shows high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.744, coverage hit ≈ 0.840, voxel recall ≈ 0.800, voxel IoU ≈ 0.271), indicating that most of the expected BIM geometry is captured in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was previously assessed as Uncertain at the earlier time step (t-1). Considering these 4 types of information together, the element is assessed as Completed. | Completed | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that the view is relatively distant and only one side of the wall is observed, but a skirting/baseboard-like structure appears to be present on the visible side. The point cloud summary shows high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.919, coverage hit ≈ 0.909, voxel recall ≈ 0.900, voxel IoU ≈ 0.214), indicating that most of the expected BIM geometry is captured in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Completed at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Completed.
3osoug9Ev0g85atawY75eN | 2802365 | IfcBuildingElementProxy | 2802365 | FFL\IfcBuildingElementProxy\2802365__3osoug9Ev0g85atawY75eN\meta.json | Baseboard installation | Not Started | A total of 3 types of input information are considered in the assessment, while temporal context information is not available. The local images indicate that both sides of the wall are clearly observed, no skirting/baseboard is visible, and the wall remains at an early construction stage with exposed steel framing. The point cloud summary shows moderate geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.737, coverage hit ≈ 0.738, voxel recall ≈ 0.667, voxel IoU ≈ 0.145), suggesting that surrounding wall geometry is captured but not the specific skirting element. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. Considering these 3 types of information together, the element is assessed as Not Started. | Not Started | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that only one side of the wall is observed at this time step and no skirting/baseboard is visible on the observed surface. The point cloud summary shows relatively high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.745, coverage hit ≈ 0.745, voxel recall ≈ 0.833, voxel IoU ≈ 0.417), suggesting that nearby wall geometry is well captured in the scan. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Not Started. | Not Started | A total of 4 types of input information are considered in the assessment, while no information is missing. The local images indicate that no skirting/baseboard is visible at the expected wall location. The point cloud summary shows very high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.972, coverage hit ≈ 1.000, voxel recall ≈ 1.000, voxel IoU ≈ 0.255), indicating that the surrounding wall geometry is fully captured in the scanned data. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 4 types of information together, the element is assessed as Not Started. | Uncertain | A total of 3 types of input information are considered in the assessment, while local image information is not available. The point cloud summary shows no geometric correspondence between the BIM model and the as-built scan (coverage = 0.000, coverage hit = 0.000, voxel recall = 0.000, voxel IoU = 0.000), indicating that no relevant geometry corresponding to the BIM element is detected in the scanned data; this may also indicate that the scanner did not capture the area near the target element. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Not Started at the previous time step (t-1). Considering these 3 types of information together, the available evidence is insufficient to reliably determine the current construction status of the element, and the element is assessed as Uncertain. | Uncertain | A total of 3 types of input information are considered in the assessment, while local image information is not available. The point cloud summary shows relatively high geometric correspondence between the BIM model and the as-built scan (coverage ≈ 0.786, coverage hit ≈ 0.823, voxel recall ≈ 0.833, voxel IoU ≈ 0.312), indicating that the surrounding geometry near the BIM element is largely captured in the scan. The BIM semantics describe the element as a wall skirting/baseboard finishing component attached to the wall surface. The temporal context shows that the element was assessed as Uncertain at the previous time step (t-1). Considering these 3 types of information together, the available evidence is insufficient to reliably determine the construction status of the element, and the element is assessed as Uncertain.
3osoug9Ev0g85atawY75eM | 2802366 | IfcBuildingElementProxy | 2802366 | FFL\IfcBuildingElementProxy\2802366__3osoug9Ev0g85atawY75eM\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75eL | 2802367 | IfcBuildingElementProxy | 2802367 | FFL\IfcBuildingElementProxy\2802367__3osoug9Ev0g85atawY75eL\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75eJ | 2802369 | IfcBuildingElementProxy | 2802369 | FFL\IfcBuildingElementProxy\2802369__3osoug9Ev0g85atawY75eJ\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75eH | 2802371 | IfcBuildingElementProxy | 2802371 | FFL\IfcBuildingElementProxy\2802371__3osoug9Ev0g85atawY75eH\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75eG | 2802372 | IfcBuildingElementProxy | 2802372 | FFL\IfcBuildingElementProxy\2802372__3osoug9Ev0g85atawY75eG\meta.json | Baseboard installation | Not Started |  | Not Started |  | Uncertain |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75fo | 2802402 | IfcBuildingElementProxy | 2802402 | FFL\IfcBuildingElementProxy\2802402__3osoug9Ev0g85atawY75fo\meta.json | Baseboard installation | Not Started | Judging by the local images, the walls have not yet been properly constructed. | Not Started |  | Not Started |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75fn | 2802403 | IfcBuildingElementProxy | 2802403 | FFL\IfcBuildingElementProxy\2802403__3osoug9Ev0g85atawY75fn\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75fm | 2802404 | IfcBuildingElementProxy | 2802404 | FFL\IfcBuildingElementProxy\2802404__3osoug9Ev0g85atawY75fm\meta.json | Baseboard installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75eW | CT-FD | IfcBuildingElementProxy | SE_NHOST_MED_TRACK-CT-L-SHP_USER_300:CT-FD:2802324 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802324__3osoug9Ev0g85atawY75eW\meta.json | Curtain Track Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75hX | CT1 | IfcBuildingElementProxy | SE_NHOST_ANCL_CURT_USER_CT_200:CT1:2802259 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802259__3osoug9Ev0g85atawY75hX\meta.json | Curtain Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain | The local image is unclear. | Uncertain | The local image is blocked by the door.
1HhZYu__jDIBU58mznPsIW | DGD | IfcBuildingElementProxy | SE_NHOST_CLIN_GLOVE-DISP_GENC_DGD_300:DGD:4115567 | WAREHOUSE LEVEL\IfcBuildingElementProxy\4115567__1HhZYu__jDIBU58mznPsIW\meta.json | Glove Dispenser Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain
1HhZYu__jDIBU58mznPsI$ | DH | IfcBuildingElementProxy | SE_NHOST_TOIL_DISINF-HOLD_GENC_DH_300:DH:4115568 | WAREHOUSE LEVEL\IfcBuildingElementProxy\4115568__1HhZYu__jDIBU58mznPsI$\meta.json | Disinfectant Holder Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain
3osoug9Ev0g85atawY75fl | HAND SENSOR-n3 | IfcBuildingElementProxy | EF_FACE_DR-SENSOR_2:HAND SENSOR-n3:2802389 | FFL\IfcBuildingElementProxy\2802389__3osoug9Ev0g85atawY75fl\meta.json | Switch Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75fr | HAND SENSOR-n3 | IfcBuildingElementProxy | EF_FACE_DR-SENSOR_2:HAND SENSOR-n3:2802399 | FFL\IfcBuildingElementProxy\2802399__3osoug9Ev0g85atawY75fr\meta.json | Switch Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75kZ | HAND SENSOR-n3 | IfcBuildingElementProxy | EF_FACE_DR-SENSOR_2:HAND SENSOR-n3:2802449 | FFL\IfcBuildingElementProxy\2802449__3osoug9Ev0g85atawY75kZ\meta.json | Switch Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain | The local image is too blurry. | Completed
3osoug9Ev0g85atawY75em | HBHT-1 | IfcBuildingElementProxy | SE_WALL_CLIN_BEDHD-TRUNK_HORZ_HBHT_1:HBHT-1:2802340 | FFL\IfcBuildingElementProxy\2802340__3osoug9Ev0g85atawY75em\meta.json | Hospital Bed Head Trunking Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain | The local image is too blurry. | Uncertain | The projection might be incorrect.What is being projected is the room next door.
3osoug9Ev0g85atawY75kb | KICK-n6 | IfcBuildingElementProxy | EF_FACE_DR-SENSOR_2:KICK-n6:2802447 | FFL\IfcBuildingElementProxy\2802447__3osoug9Ev0g85atawY75kb\meta.json | Switch Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Completed
3osoug9Ev0g85atawY75kX | KICK-n6 | IfcBuildingElementProxy | EF_FACE_DR-SENSOR_2:KICK-n6:2802451 | FFL\IfcBuildingElementProxy\2802451__3osoug9Ev0g85atawY75kX\meta.json | Switch Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain | The local image is too blurry. | Completed | Some of the photos project images of the adjacent room.
3osoug9Ev0g85atawY75hr | MAMMO UNIT | IfcBuildingElementProxy | SE_NHOST_MED_MAMMO-UNIT_USER_300:MAMMO UNIT:2802271 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802271__3osoug9Ev0g85atawY75hr\meta.json | Medical Equipment Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Not Started
3osoug9Ev0g85atawY75hq | MMMI-162 CONSOLE control, mammography | IfcBuildingElementProxy | SPE_SYSTEM_radiology_mammography_control:MMMI-162 CONSOLE control, mammography:2802272 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802272__3osoug9Ev0g85atawY75hq\meta.json | Medical Equipment Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Not Started
3osoug9Ev0g85atawY75fg | PTD | IfcBuildingElementProxy | SE_NHOST_TOIL_PT-DISP_GENC_PTD_300:PTD:2802394 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802394__3osoug9Ev0g85atawY75fg\meta.json | Toilet Accessories Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain | The projection might be incorrect.
3osoug9Ev0g85atawY75kc | RCK-LA | IfcBuildingElementProxy | SE_NHOST_MED_LEAD-APRON-RACK_GENC_RCK-LA_Type 2_300:RCK-LA:2802446 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802446__3osoug9Ev0g85atawY75kc\meta.json | Lead Apron Rack Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Not Started
3osoug9Ev0g85atawY75fh | SD | IfcBuildingElementProxy | SE_NHOST_TOIL_SOAP-DISP_SD_300:SD:2802393 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802393__3osoug9Ev0g85atawY75fh\meta.json | Soap Dispenser Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain | The projection might be incorrect.What is being projected is the room next door.
3osoug9Ev0g85atawY75e$ | TXRV 2 | IfcBuildingElementProxy | SE_NHOST_MED_XRAY-VIEWER_TWIN_TXRV_1:TXRV 2:2802341 | WAREHOUSE LEVEL\IfcBuildingElementProxy\2802341__3osoug9Ev0g85atawY75e$\meta.json | Medical Equipment Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Not Started
1H_W1MK9v2XO5RAPjM$KBC | XRV-1 | IfcBuildingElementProxy | SE_NHOST_MED_X-RAY-VIEW_USER_XRV-1_300:XRV-1:5166078 | FFL\IfcBuildingElementProxy\5166078__1H_W1MK9v2XO5RAPjM$KBC\meta.json | Medical Equipment Installation | Not Started |  | Not Started |  | Not Started |  | Uncertain |  | Uncertain | The projection might be incorrect.What is being projected is the room next door.

## IfcColumn
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75kf | 90x90SHS | IfcColumn | SHS-Column_Shared:90x90SHS:2802459 | WAREHOUSE LEVEL\IfcColumn\2802459__3osoug9Ev0g85atawY75kf\meta.json | Column Encasement and Finishing | Low | This member is an interior, load-bearing SHS steel column (90x90 SHS). In the 2025-02-10 site views, the surrounding area is still at an early unfinished construction stage; the column line is present, but the room is far from its final enclosed condition. The detected as-built cluster is much wider than the 90x90 BIM profile, which indicates contamination from adjacent partition and wall surfaces rather than a clean match to a finished column condition. Point cloud comparison reports coverage_grid 87.2%, coverage_hit 93.4%, and voxel_recall 50.0%. In engineering terms, the structural member is likely already erected, but the observable column encasement and finishing stage is still early, so the completion level is rated Low. | Medium | By 2025-03-17, the column zone is more consistently formed and more of the vertical enclosure around the member is visible, but the area still reads as under active fit-out rather than fully finished. Because the extracted segment still contains nearby wall surfaces, the overlap should not be interpreted as full completion of the column finish package. The metrics are coverage_grid 80.7%, coverage_hit 89.7%, and voxel_recall 57.7%. Accordingly, the encasement and finishing status is assessed as Medium. | High | On 2025-04-11, the BIM column location is strongly aligned with the as-built vertical element and the local enclosure has been substantially established. Point cloud metrics increase to coverage_grid 95.3%, coverage_hit 100.0%, and voxel_recall 88.5%, which is consistent with a near-final column condition according to the design intent. However, the room has not yet reached the fully finished appearance visible later, so the completion level is judged High rather than Completed. | High | The 2025-06-02 dataset is incomplete and cannot support a direct engineering assessment. The asbuilt_segmented.pcd is empty, processed_mesh_local.ply is missing, and the summary returns coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0% because no usable as-built points were written. This is a data-availability problem, not evidence that the column regressed on site. Since the same object is already High on 2025-04-11 and reaches Completed on 2025-08-01, the most defensible monotonic inference is to keep this date at High. | Completed | By 2025-08-01, the room is in a finished clinical-room condition and this column zone is fully absorbed into the final enclosure. Although the segmented point cloud still contains nearby surfaces and direct exposure of the steel is reduced, the overall construction context supports a completed encasement and finishing state. The point cloud summary reports coverage_grid 99.6%, coverage_hit 100.0%, and voxel_recall 53.8%. On balance, the completion level is rated Completed.
3osoug9Ev0g85atawY75kg | 90x90SHS | IfcColumn | SHS-Column_Shared:90x90SHS:2802458 | WAREHOUSE LEVEL\IfcColumn\2802458__3osoug9Ev0g85atawY75kg\meta.json | Column Encasement and Finishing | Low | This object is also an interior structural SHS column carrying load within the room. In the 2025-02-10 images, the space is still largely at shell-and-partition stage, with only partial readability of the column zone. The detected as-built body is significantly larger than the planned 90x90 profile, so the strong overlap values are being inflated by adjacent wall and enclosure geometry rather than indicating a finished column build-up. The point cloud summary shows coverage_grid 89.4%, coverage_hit 92.6%, and voxel_recall 50.0%. Therefore, from a construction-status perspective, the column encasement and finishing should be labeled Low. | Medium | At 2025-03-17, the column position is more legible and the surrounding partition works are further advanced, but the component still does not present as a completed finished-room column. Because segmentation spillover from nearby surfaces remains evident, the match quality should be read cautiously rather than as final completion. The recorded values are coverage_grid 81.4%, coverage_hit 89.5%, and voxel_recall 53.8%. This supports a Medium rating for the column encasement and finishing stage. | High | By 2025-04-11, the vertical element corresponding to this BIM column is well established and the surrounding enclosure is largely in place. The point cloud metrics improve to coverage_grid 97.0%, coverage_hit 100.0%, and voxel_recall 96.2%, indicating strong geometric agreement with the planned location. Even so, the final finished-room condition is better evidenced at the later date, so the status is judged High rather than Completed. | High | The 2025-06-02 record is not reliable for direct assessment. The segmented PCD is empty, the local mesh is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. These zeros reflect missing scan output rather than physical removal or non-installation of the column. Given the chronological logic between High on 2025-04-11 and Completed on 2025-08-01, this date is reasonably inferred as High. | Completed | On 2025-08-01, the surrounding room finishes are complete and this column zone has been fully integrated into the final architectural enclosure. The later segmentation still picks up nearby surfaces, so voxel_recall remains 53.8%, but the overall condition reads as complete in context. The summary gives coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 53.8%. Therefore, the completion level is rated Completed.

## IfcDoor
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75eE | 0_A_L-L | IfcDoor | DR_NHOST_PNL_GENC_300:0_A_L-L:2802358 | WAREHOUSE LEVEL\IfcDoor\2802358__3osoug9Ev0g85atawY75eE\meta.json | Door Installation | Low | This BIM item represents an interior non-host panel door assembly, planned at about 1.07 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 24.2%, coverage_hit 20.3%, and voxel_recall 24.5%. In summary, the installation is classified as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Low | This BIM item represents an interior non-host panel door assembly, planned at about 1.07 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. By mid-March the surrounding partition work is more advanced, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 25.4%, coverage_hit 22.0%, and voxel_recall 25.2%. In summary, the installation is classified as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This component is an interior non-host panel door assembly, planned at about 1.07 m wide and 2.16 m high. By mid-April the room enclosure is largely established, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 40.2%, coverage_hit 36.9%, and voxel_recall 45.0%. The completion is therefore assessed as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Medium | This object is an interior non-host panel door assembly, planned at about 1.07 m wide and 2.16 m high. In the June fit-out capture, the capture is sparse and partly occluded, but the opening/frame zone is still present and more advanced than the early shell condition; the measured alignment is coverage_grid 9.3%, coverage_hit 7.1%, and voxel_recall 6.0%. The completion is therefore judged as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Completed | This element is an interior non-host panel door assembly, planned at about 1.07 m wide and 2.16 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 96.2%, coverage_hit 99.3%, and voxel_recall 50.3%. Although the final scan is partly occluded, the finished-room imagery and the stable alignment to the planned opening indicate that the lower percentages are caused by view limitation rather than a missing door. Accordingly, the door assembly is rated as Completed (100%).
3osoug9Ev0g85atawY75fZ | 0_A_L-L | IfcDoor | DR_NHOST_PNL_GENC_300:0_A_L-L:2802385 | WAREHOUSE LEVEL\IfcDoor\2802385__3osoug9Ev0g85atawY75fZ\meta.json | Door Installation | Low | This BIM item represents an interior non-host panel door assembly, planned at about 0.92 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 27.3%, coverage_hit 20.6%, and voxel_recall 32.4%. In summary, the installation is classified as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Low | This BIM item represents an interior non-host panel door assembly, planned at about 0.92 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. By mid-March the surrounding partition work is more advanced, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 26.2%, coverage_hit 25.0%, and voxel_recall 28.2%. In summary, the installation is classified as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This component is an interior non-host panel door assembly, planned at about 0.92 m wide and 2.16 m high. By mid-April the room enclosure is largely established, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 33.8%, coverage_hit 27.1%, and voxel_recall 42.3%. The completion is therefore assessed as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | High | This object is an interior non-host panel door assembly, planned at about 0.92 m wide and 2.16 m high. In the June fit-out capture, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 84.2%, coverage_hit 91.6%, and voxel_recall 93.0%. In engineering terms this supports a judged as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | Completed | This element is an interior non-host panel door assembly, planned at about 0.92 m wide and 2.16 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 55.4%, coverage_hit 46.0%, and voxel_recall 60.6%. Although the final scan is partly occluded, the finished-room imagery and the stable alignment to the planned opening indicate that the lower percentages are caused by view limitation rather than a missing door. Accordingly, the door assembly is rated as Completed (100%).
3osoug9Ev0g85atawY75e4 | 0_A_L-L | IfcDoor | DR_NHOST_PNL_GENC_300:0_A_L-L:2802352 | WAREHOUSE LEVEL\IfcDoor\2802352__3osoug9Ev0g85atawY75e4\meta.json | Door Installation | Low | This element is an interior non-host panel door assembly, planned at about 0.65 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 20.6%, coverage_hit 15.9%, and voxel_recall 35.4%. In summary, the installation is rated as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This element is an interior non-host panel door assembly, planned at about 0.65 m wide and 2.16 m high. By mid-March the surrounding partition work is more advanced, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 52.7%, coverage_hit 49.1%, and voxel_recall 45.8%. The completion is therefore rated as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Medium | This object is an interior non-host panel door assembly, planned at about 0.65 m wide and 2.16 m high. By mid-April the room enclosure is largely established, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 25.3%, coverage_hit 12.1%, and voxel_recall 31.2%. The completion is therefore judged as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Medium | This component is an interior non-host panel door assembly, planned at about 0.65 m wide and 2.16 m high. In the June fit-out capture, the capture is sparse and partly occluded, but the opening/frame zone is still present and more advanced than the early shell condition; the measured alignment is coverage_grid 23.1%, coverage_hit 18.9%, and voxel_recall 14.6%. The completion is therefore assessed as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Completed | This BIM item represents an interior non-host panel door assembly, planned at about 0.65 m wide and 2.16 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final imagery and the point cloud both indicate a fully installed door in the planned opening. Accordingly, the door assembly is classified as Completed (100%).
3osoug9Ev0g85atawY75e5 | 0_A_L-L | IfcDoor | DR_NHOST_PNL_GENC_300:0_A_L-L:2802351 | WAREHOUSE LEVEL\IfcDoor\2802351__3osoug9Ev0g85atawY75e5\meta.json | Door Installation | Low | This object is an interior non-host panel door assembly, planned at about 0.96 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 25.3%, coverage_hit 24.8%, and voxel_recall 33.3%. In summary, the installation is judged as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Low | This object is an interior non-host panel door assembly, planned at about 0.96 m wide and 2.16 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. By mid-March the surrounding partition work is more advanced, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 25.3%, coverage_hit 22.5%, and voxel_recall 0.0%. In summary, the installation is judged as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This BIM item represents an interior non-host panel door assembly, planned at about 0.96 m wide and 2.16 m high. By mid-April the room enclosure is largely established, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 23.3%, coverage_hit 20.6%, and voxel_recall 30.6%. The completion is therefore classified as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Medium | This element is an interior non-host panel door assembly, planned at about 0.96 m wide and 2.16 m high. In the June fit-out capture, the capture is sparse and partly occluded, but the opening/frame zone is still present and more advanced than the early shell condition; the measured alignment is coverage_grid 6.0%, coverage_hit 4.8%, and voxel_recall 5.6%. The completion is therefore rated as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Completed | This component is an interior non-host panel door assembly, planned at about 0.96 m wide and 2.16 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 98.4%, coverage_hit 92.4%, and voxel_recall 84.7%. The final imagery and the point cloud both indicate a fully installed door in the planned opening. Accordingly, the door assembly is assessed as Completed (100%).
3osoug9Ev0g85atawY75eF | STANDARD | IfcDoor | DR_WALL_FR_REBATED_300:STANDARD:2802357 | WAREHOUSE LEVEL\IfcDoor\2802357__3osoug9Ev0g85atawY75eF\meta.json | Door Installation | Low | This component is an interior rebated wall door assembly, planned at about 1.15 m wide and 2.20 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 38.8%, coverage_hit 44.2%, and voxel_recall 27.3%. In summary, the installation is assessed as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This component is an interior rebated wall door assembly, planned at about 1.15 m wide and 2.20 m high. By mid-March the surrounding partition work is more advanced, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 79.0%, coverage_hit 95.0%, and voxel_recall 51.8%. The completion is therefore assessed as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | High | This element is an interior rebated wall door assembly, planned at about 1.15 m wide and 2.20 m high. By mid-April the room enclosure is largely established, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 80.3%, coverage_hit 98.8%, and voxel_recall 62.7%. In engineering terms this supports a rated as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | High | This BIM item represents an interior rebated wall door assembly, planned at about 1.15 m wide and 2.20 m high. In the June fit-out capture, the June scan is thin and partly occluded, but the door position remains aligned with the planned opening and the surrounding fit-out is already well advanced; the point-cloud metrics are coverage_grid 35.9%, coverage_hit 33.5%, and voxel_recall 18.2%. In engineering terms this supports a classified as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | Completed | This object is an interior rebated wall door assembly, planned at about 1.15 m wide and 2.20 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 90.5%, coverage_hit 95.4%, and voxel_recall 72.7%. Although the final scan is partly occluded, the finished-room imagery and the stable alignment to the planned opening indicate that the lower percentages are caused by view limitation rather than a missing door. Accordingly, the door assembly is judged as Completed (100%).
3osoug9Ev0g85atawY75e6 | STANDARD | IfcDoor | DR_WALL_FR_REBATED_300:STANDARD:2802350 | WAREHOUSE LEVEL\IfcDoor\2802350__3osoug9Ev0g85atawY75e6\meta.json | Door Installation | Medium | This BIM item represents an interior rebated wall door assembly, planned at about 1.70 m wide and 2.20 m high. At this early shell and partition stage, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 83.0%, coverage_hit 92.5%, and voxel_recall 88.4%. The completion is therefore classified as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | Medium | This BIM item represents an interior rebated wall door assembly, planned at about 1.70 m wide and 2.20 m high. By mid-March the surrounding partition work is more advanced, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 76.9%, coverage_hit 81.5%, and voxel_recall 62.3%. The completion is therefore classified as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | High | This component is an interior rebated wall door assembly, planned at about 1.70 m wide and 2.20 m high. By mid-April the room enclosure is largely established, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 77.3%, coverage_hit 98.3%, and voxel_recall 87.0%. In engineering terms this supports a assessed as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | High | This object is an interior rebated wall door assembly, planned at about 1.70 m wide and 2.20 m high. In the June fit-out capture, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 69.4%, coverage_hit 73.0%, and voxel_recall 55.1%. In engineering terms this supports a judged as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | Completed | This element is an interior rebated wall door assembly, planned at about 1.70 m wide and 2.20 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 97.7%, coverage_hit 99.9%, and voxel_recall 98.6%. The final imagery and the point cloud both indicate a fully installed door in the planned opening. Accordingly, the door assembly is rated as Completed (100%).
3osoug9Ev0g85atawY75e0 | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802356 | WAREHOUSE LEVEL\IfcDoor\2802356__3osoug9Ev0g85atawY75e0\meta.json | Door Louver Installation | Low | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore rated as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-March the surrounding partition work is more advanced, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore rated as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-April the room enclosure is largely established, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore judged as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the Low condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as Medium (33-66%) to keep a logical construction progression. | Completed | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final point cloud closely matches the planned louver and the host door is in finished condition. Therefore the louver installation is classified as Completed (100%).
3osoug9Ev0g85atawY75fW | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802388 | WAREHOUSE LEVEL\IfcDoor\2802388__3osoug9Ev0g85atawY75fW\meta.json | Door Louver Installation | Low | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore assessed as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-March the surrounding partition work is more advanced, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 55.0%, coverage_hit 66.7%, and voxel_recall 33.3%. This supports a assessed as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | Medium | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-April the room enclosure is largely established, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 40.0%, coverage_hit 50.0%, and voxel_recall 33.3%. This supports a rated as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | High | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. In the June fit-out capture, the door face is largely formed and the louver location aligns well with the BIM item; the point-cloud metrics are coverage_grid 36.4%, coverage_hit 33.3%, and voxel_recall 33.3%. For a small recessed feature, the remaining mismatch is consistent with occlusion and sparse sampling, so the louver is classified as High (66-99%). | Completed | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 50.0%, coverage_hit 50.0%, and voxel_recall 33.3%. The final scan only captures part of this small accessory, but the finished host door and the persistent alignment to the planned louver location support completion. Therefore the louver installation is judged as Completed (100%).
3osoug9Ev0g85atawY75eC | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802360 | WAREHOUSE LEVEL\IfcDoor\2802360__3osoug9Ev0g85atawY75eC\meta.json | Door Louver Installation | Low | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 50.0%, coverage_hit 66.7%, and voxel_recall 100.0%. The accessory is therefore judged as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-March the surrounding partition work is more advanced, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 70.0%, coverage_hit 66.7%, and voxel_recall 100.0%. This supports a judged as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | High | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-April the room enclosure is largely established, the door face is largely formed and the louver location aligns well with the BIM item; the point-cloud metrics are coverage_grid 84.6%, coverage_hit 83.3%, and voxel_recall 100.0%. For a small recessed feature, the remaining mismatch is consistent with occlusion and sparse sampling, so the louver is classified as High (66-99%). | High | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the High condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as High (66-99%) to keep a logical construction progression. | Completed | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final point cloud closely matches the planned louver and the host door is in finished condition. Therefore the louver installation is assessed as Completed (100%).
3osoug9Ev0g85atawY75fa | STANDARD | IfcDoor | DR_WALL_FR_REBATED_300:STANDARD:2802384 | WAREHOUSE LEVEL\IfcDoor\2802384__3osoug9Ev0g85atawY75fa\meta.json | Door Installation | Low | This component is an interior rebated wall door assembly, planned at about 1.00 m wide and 2.20 m high, and completion means the leaf and frame must be installed in the designed opening as a functional door set. At this early shell and partition stage, the opening and nearby wall work are visible, but the door leaf/frame are not yet convincingly installed as a usable assembly; point-cloud comparison gives coverage_grid 51.2%, coverage_hit 66.7%, and voxel_recall 60.9%. In summary, the installation is assessed as Low (0-33%) because only an early doorway condition is evidenced at this stage. | Medium | This component is an interior rebated wall door assembly, planned at about 1.00 m wide and 2.20 m high. By mid-March the surrounding partition work is more advanced, the doorway is more consistently formed and parts of the frame or door leaf geometry are present, but the assembly still reads as incomplete; the measured alignment is coverage_grid 41.4%, coverage_hit 40.5%, and voxel_recall 26.6%. The completion is therefore assessed as Medium (33-66%) because the door system is partially installed but not yet in finished-room condition. | High | This element is an interior rebated wall door assembly, planned at about 1.00 m wide and 2.20 m high. By mid-April the room enclosure is largely established, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 54.5%, coverage_hit 67.0%, and voxel_recall 54.7%. In engineering terms this supports a rated as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | High | This BIM item represents an interior rebated wall door assembly, planned at about 1.00 m wide and 2.20 m high. In the June fit-out capture, the door position aligns strongly with BIM and the room-side context indicates that the leaf/frame are largely in place; the point-cloud metrics are coverage_grid 88.0%, coverage_hit 84.3%, and voxel_recall 89.1%. In engineering terms this supports a classified as High (66-99%) because the door assembly is near-final, even if some finishes or hardware details are still not at handover condition. | Completed | This object is an interior rebated wall door assembly, planned at about 1.00 m wide and 2.20 m high. On the final August capture, the space is in finished condition and the leaf/frame are integrated into the completed wall opening; the measured match is coverage_grid 92.9%, coverage_hit 87.4%, and voxel_recall 78.1%. Although the final scan is partly occluded, the finished-room imagery and the stable alignment to the planned opening indicate that the lower percentages are caused by view limitation rather than a missing door. Accordingly, the door assembly is judged as Completed (100%).
3osoug9Ev0g85atawY75eD | STANDARD | IfcDoor | DR_FACE_ACC_DEADBOLT_GENC_300:STANDARD:2802359 | WAREHOUSE LEVEL\IfcDoor\2802359__3osoug9Ev0g85atawY75eD\meta.json | Door Deadbolt Installation | Low | This object is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m, and completion means the deadbolt hardware is mounted at the designed lock position on the finished door leaf. At this early shell and partition stage, the hardware position is too small to confirm reliably at this stage, and any overlap can still be explained by nearby door-face points rather than a true installed lockset; the available evidence reports coverage_grid 75.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The item is therefore judged as Low (0-33%) because the deadbolt itself is not yet securely evidenced. | Medium | This object is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. By mid-March the surrounding partition work is more advanced, partial correspondence is present at the lockset location, but the tiny hardware capture remains intermittent and the associated door is not yet in final condition; the measured point-cloud agreement is coverage_grid 57.1%, coverage_hit 100.0%, and voxel_recall 100.0%. This supports a judged as Medium (33-66%) because some hardware evidence exists, but the installation cannot yet be treated as near-final. | High | This BIM item represents a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. By mid-April the room enclosure is largely established, the hardware position aligns closely with the planned deadbolt and the surrounding door face is substantially formed; the metrics are coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. In summary, the deadbolt is classified as High (66-99%) because it appears substantially installed, even if the overall door condition is not yet the final handover state. | High | This element is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the High condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as High (66-99%) to keep a logical construction progression. | Completed | This component is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. On the final August capture, the associated door is in finished condition and the hardware location remains consistent with the design intent; the scan reports coverage_grid 42.9%, coverage_hit 50.0%, and voxel_recall 0.0%. Because the deadbolt is only a very small object, the lower final recall is most reasonably attributed to small-object under-capture rather than absence. The deadbolt installation is therefore assessed as Completed (100%).
3osoug9Ev0g85atawY75e3 | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802353 | WAREHOUSE LEVEL\IfcDoor\2802353__3osoug9Ev0g85atawY75e3\meta.json | Door Louver Installation | Low | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore assessed as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-March the surrounding partition work is more advanced, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore assessed as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-April the room enclosure is largely established, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore rated as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the Low condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as Medium (33-66%) to keep a logical construction progression. | Completed | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final point cloud closely matches the planned louver and the host door is in finished condition. Therefore the louver installation is judged as Completed (100%).
3osoug9Ev0g85atawY75fX | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802387 | WAREHOUSE LEVEL\IfcDoor\2802387__3osoug9Ev0g85atawY75fX\meta.json | Door Louver Installation | Low | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 30.0%, coverage_hit 33.3%, and voxel_recall 50.0%. The accessory is therefore rated as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-March the surrounding partition work is more advanced, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 75.0%, coverage_hit 66.7%, and voxel_recall 50.0%. This supports a rated as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | Medium | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-April the room enclosure is largely established, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 40.0%, coverage_hit 50.0%, and voxel_recall 50.0%. This supports a judged as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | High | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. In the June fit-out capture, the door face is largely formed and the louver location aligns well with the BIM item; the point-cloud metrics are coverage_grid 92.3%, coverage_hit 100.0%, and voxel_recall 100.0%. For a small recessed feature, the remaining mismatch is consistent with occlusion and sparse sampling, so the louver is assessed as High (66-99%). | Completed | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 55.6%, coverage_hit 83.3%, and voxel_recall 50.0%. The final scan only captures part of this small accessory, but the finished host door and the persistent alignment to the planned louver location support completion. Therefore the louver installation is classified as Completed (100%).
3osoug9Ev0g85atawY75eB | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802361 | WAREHOUSE LEVEL\IfcDoor\2802361__3osoug9Ev0g85atawY75eB\meta.json | Door Louver Installation | Low | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 50.0%, coverage_hit 66.7%, and voxel_recall 100.0%. The accessory is therefore rated as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-March the surrounding partition work is more advanced, the surrounding door zone is more developed and there is partial correspondence at the intended louver position, but the grille feature is still only partly evidenced; the measured overlap is coverage_grid 45.5%, coverage_hit 50.0%, and voxel_recall 0.0%. This supports a rated as Medium (33-66%) because the accessory appears to be emerging, yet it is not fully confirmed in final condition. | High | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. By mid-April the room enclosure is largely established, the door face is largely formed and the louver location aligns well with the BIM item; the point-cloud metrics are coverage_grid 63.6%, coverage_hit 83.3%, and voxel_recall 100.0%. For a small recessed feature, the remaining mismatch is consistent with occlusion and sparse sampling, so the louver is judged as High (66-99%). | High | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the High condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as High (66-99%) to keep a logical construction progression. | Completed | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 45.5%, coverage_hit 33.3%, and voxel_recall 0.0%. The final scan only captures part of this small accessory, but the finished host door and the persistent alignment to the planned louver location support completion. Therefore the louver installation is classified as Completed (100%).
3osoug9Ev0g85atawY75fY | STANDARD | IfcDoor | DR_FACE_ACC_DEADBOLT_GENC_300:STANDARD:2802386 | WAREHOUSE LEVEL\IfcDoor\2802386__3osoug9Ev0g85atawY75fY\meta.json | Door Deadbolt Installation | Low | This object is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m, and completion means the deadbolt hardware is mounted at the designed lock position on the finished door leaf. At this early shell and partition stage, the hardware position is too small to confirm reliably at this stage, and any overlap can still be explained by nearby door-face points rather than a true installed lockset; the available evidence reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The item is therefore judged as Low (0-33%) because the deadbolt itself is not yet securely evidenced. | Medium | This object is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. By mid-March the surrounding partition work is more advanced, partial correspondence is present at the lockset location, but the tiny hardware capture remains intermittent and the associated door is not yet in final condition; the measured point-cloud agreement is coverage_grid 73.3%, coverage_hit 100.0%, and voxel_recall 25.0%. This supports a judged as Medium (33-66%) because some hardware evidence exists, but the installation cannot yet be treated as near-final. | Medium | This BIM item represents a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. By mid-April the room enclosure is largely established, partial correspondence is present at the lockset location, but the tiny hardware capture remains intermittent and the associated door is not yet in final condition; the measured point-cloud agreement is coverage_grid 42.9%, coverage_hit 25.0%, and voxel_recall 25.0%. This supports a classified as Medium (33-66%) because some hardware evidence exists, but the installation cannot yet be treated as near-final. | High | This element is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. In the June fit-out capture, the hardware position aligns closely with the planned deadbolt and the surrounding door face is substantially formed; the metrics are coverage_grid 37.5%, coverage_hit 50.0%, and voxel_recall 50.0%. In summary, the deadbolt is rated as High (66-99%) because it appears substantially installed, even if the overall door condition is not yet the final handover state. | Completed | This component is a door deadbolt accessory, planned at about 0.06 x 0.04 x 0.04 m. On the final August capture, the associated door is in finished condition and the hardware location remains consistent with the design intent; the scan reports coverage_grid 62.5%, coverage_hit 75.0%, and voxel_recall 25.0%. Because the deadbolt is only a very small object, the lower final recall is most reasonably attributed to small-object under-capture rather than absence. The deadbolt installation is therefore assessed as Completed (100%).
3osoug9Ev0g85atawY75e1 | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802355 | WAREHOUSE LEVEL\IfcDoor\2802355__3osoug9Ev0g85atawY75e1\meta.json | Door Louver Installation | Low | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore judged as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-March the surrounding partition work is more advanced, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore judged as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-April the room enclosure is largely established, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore classified as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the Low condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as Medium (33-66%) to keep a logical construction progression. | Completed | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final point cloud closely matches the planned louver and the host door is in finished condition. Therefore the louver installation is assessed as Completed (100%).
3osoug9Ev0g85atawY75e2 | STANDARD | IfcDoor | DR_FACE_ACC_LVR_GENC_300:STANDARD:2802354 | WAREHOUSE LEVEL\IfcDoor\2802354__3osoug9Ev0g85atawY75e2\meta.json | Door Louver Installation | Low | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. At this early shell and partition stage, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore classified as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This BIM item represents a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-March the surrounding partition work is more advanced, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore classified as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Low | This component is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is based on the louver itself being fitted to the door face rather than the doorway existing around it. By mid-April the room enclosure is largely established, the host doorway may be visible, but the small louver grille itself is not yet reliably confirmed at the target location; the point-cloud evidence is coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. The accessory is therefore assessed as Low (0-33%) because there is still insufficient direct evidence of the installed louver. | Medium | This object is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m, and completion is judged on the specific accessory or door assembly rather than the surrounding wall alone. The 2025-06-02 scan is incomplete for this item: asbuilt_segmented.pcd is effectively empty at 164 bytes, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, and voxel_recall 0.0%. Given the Low condition on 2025-04-11 and the Completed condition on 2025-08-01, this date is inferred as Medium (33-66%) to keep a logical construction progression. | Completed | This element is a door-face louver accessory, planned at about 0.15 x 0.07 x 0.05 m. On the final August capture, the host door is in its finished state and the target louver position is supported by coverage_grid 100.0%, coverage_hit 100.0%, and voxel_recall 100.0%. The final point cloud closely matches the planned louver and the host door is in finished condition. Therefore the louver installation is rated as Completed (100%).

## IfcFlowTerminal
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75ff | STANDARD | IfcFlowTerminal | PB_NHOST_FAUCET_BASIN_WALL_300:STANDARD:2802395 | WAREHOUSE LEVEL\IfcFlowTerminal\2802395__3osoug9Ev0g85atawY75ff\meta.json | Wall-Mounted Faucet Installation | Not Started | Only wall framing and finish preparation are visible; the faucet is not installed. | Low | Wall finishes and the faucet outlet location are visible, but the fixture is not mounted. | Low | The wall is finished and the outlet point is present, but the faucet is still missing. |  | The current scan data is incomplete | Completed | The wall-mounted faucet is visibly installed in the finished washroom.
3osoug9Ev0g85atawY75eh | TL 2 | IfcFlowTerminal | LF_NHOST_BUILT-IN_DN_TL_1:TL 2:2802329 | WAREHOUSE LEVEL\IfcFlowTerminal\2802329__3osoug9Ev0g85atawY75eh\meta.json | Towel Rail Installation | Not Started | Only the wall area is visible; the accessory is not yet identifiable. | Medium | The rail profile is visible, but the surrounding finish still looks unfinished. | High | The rail is visible on the finished wall, with only minor uncertainty from limited scan coverage. |  | The current scan data is incomplete | Completed | The rail is clearly installed on the finished wall.
3osoug9Ev0g85atawY75ef | TL 2 | IfcFlowTerminal | LF_NHOST_BUILT-IN_DN_TL_1:TL 2:2802331 | WAREHOUSE LEVEL\IfcFlowTerminal\2802331__3osoug9Ev0g85atawY75ef\meta.json | Towel Rail Installation | Not Started | Only the wall area is visible; the accessory is not yet identifiable. | Medium | The rail profile is visible, but the surrounding finish still looks unfinished. | High | The rail is visible on the finished wall, with only minor uncertainty from limited scan coverage. |  | The current scan data is incomplete | Completed | The rail is clearly installed on the finished wall.
3osoug9Ev0g85atawY75fi | U2D | IfcFlowTerminal | PB_NHOST_BASIN_WASH-HD_300:U2D:2802392 | WAREHOUSE LEVEL\IfcFlowTerminal\2802392__3osoug9Ev0g85atawY75fi\meta.json | Wash Basin Installation | Not Started | The washroom enclosure is incomplete and no basin is present. | Low | The basin location is formed, but the basin body is not yet installed. | High | The basin area is largely formed and the fixture body is mostly in place, though final completion is reached later. |  | The current scan data is incomplete | Completed | The wash basin is clearly installed and integrated with the finished washroom.

## IfcFurnishingElement
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75hp | BH | IfcFurnishingElement | CK_NHOST_BH_GENC_300:BH:2802273 | WAREHOUSE LEVEL\IfcFurnishingElement\2802273__3osoug9Ev0g85atawY75hp\meta.json | Bulkhead Installation | Medium | The bulkhead form is already visible, but the enclosure and finish are still incomplete. | High | The bulkhead is continuous and largely formed, with only finish work remaining. | High | The bulkhead remains in place and visually near completion, though the scan is partially occluded. |  | The current scan data is incomplete. | Completed | The bulkhead is fully formed and visually finished.
3osoug9Ev0g85atawY75hh | BH | IfcFurnishingElement | CK_NHOST_BH_GENC_300:BH:2802265 | WAREHOUSE LEVEL\IfcFurnishingElement\2802265__3osoug9Ev0g85atawY75hh\meta.json | Bulkhead Installation | Medium | The bulkhead form is already visible, but the enclosure and finish are still incomplete. | High | The bulkhead is continuous and largely formed, with only finish work remaining. | High | The bulkhead remains in place and visually near completion, though the scan is partially occluded. |  | The current scan data is incomplete. | Completed | The bulkhead is fully formed and visually finished.
3osoug9Ev0g85atawY75en | CABINET-MOBILE 600X1000 | IfcFurnishingElement | FUR_NDHK_CABINET_mobile_USER:CABINET-MOBILE 600X1000:2802339 | WAREHOUSE LEVEL\IfcFurnishingElement\2802339__3osoug9Ev0g85atawY75en\meta.json | Mobile Cabinet Installation | Not Started | The designated cabinet footprint is empty and no mobile cabinet is visible. | Not Started | The designated cabinet footprint is still empty and no cabinet is present. | Not Started | The room is advancing, but the cabinet location remains empty. |  | The current scan data is incomplete. | Not Started | The room is finished, but the designated mobile-cabinet footprint is still empty.
3osoug9Ev0g85atawY75hs | CH 2 | IfcFurnishingElement | FN_SEAT_SWIV_USER_CH_1:CH 2:2802270 | WAREHOUSE LEVEL\IfcFurnishingElement\2802270__3osoug9Ev0g85atawY75hs\meta.json | Swivel Chair Installation | Not Started | The designated chair location is empty and no swivel chair is visible. | Not Started | The designated chair location is still empty with no chair present. | Not Started | The area is more finished, but the swivel chair is still missing. |  | The current scan data is incomplete. | Not Started | The room is finished, but no swivel chair is present at the designated location.
3osoug9Ev0g85atawY75ht | CH 2 | IfcFurnishingElement | FN_SEAT_SWIV_USER_CH_1:CH 2:2802269 | WAREHOUSE LEVEL\IfcFurnishingElement\2802269__3osoug9Ev0g85atawY75ht\meta.json | Swivel Chair Installation | Not Started | The designated chair location is empty and no swivel chair is visible. | Not Started | The designated chair location is still empty with no chair present. | Not Started | The area is more finished, but the swivel chair is still missing. |  | The current scan data is incomplete. | Not Started | The room is finished, but no swivel chair is present at the designated location.
3osoug9Ev0g85atawY75e_ | CH-P | IfcFurnishingElement | FN_SEAT_SIDE_USER_CH-P_1:CH-P:2802342 | WAREHOUSE LEVEL\IfcFurnishingElement\2802342__3osoug9Ev0g85atawY75e_\meta.json | Side Chair Installation | Not Started | The designated chair footprint is empty and no side chair is visible. | Not Started | The designated chair footprint is still empty with no chair present. | Not Started | The room is progressing, but the side chair is still not installed. |  | The current scan data is incomplete. | Not Started | The room is finished, but no side chair is present at the designated location.
3osoug9Ev0g85atawY75hi | FHC-1/T/1000 | IfcFurnishingElement | CK_NHOST_FHC-1_4D_300:FHC-1/T/1000:2802264 | WAREHOUSE LEVEL\IfcFurnishingElement\2802264__3osoug9Ev0g85atawY75hi\meta.json | Fire Hose Cabinet Installation | Low | The cabinet opening and location are present, but the cabinet assembly is not finished. | Medium | The wall opening and cabinet zone are formed, but the final cabinet finish is still incomplete. | High | The cabinet assembly is largely installed, with the final finished appearance reached later. |  | The current scan data is incomplete. | Completed | The fire hose cabinet is visibly installed in the finished wall.
2upq7GGGf6pP7NZOlHPr7c | IPS_RECE | IfcFurnishingElement | CK_NHOST_IPS_RECE_300:IPS_RECE:2802391 | WAREHOUSE LEVEL\IfcFurnishingElement\2802391__2upq7GGGf6pP7NZOlHPr7c\meta.json | Recessed Access Panel Installation | Low | The recessed opening is visible, but the access panel is not yet complete. | Medium | The panel frame and door are partially formed, but the finish is still incomplete. | Completed | The recessed access panel is visibly installed and reads as complete. | Completed | The current scan data is incomplete. Infering from other data. | Completed | The current scan data is incomplete.
3osoug9Ev0g85atawY75fs | WB | IfcFurnishingElement | FN_NHOST_WASTE-BIN_USER_WB_300:WB:2802398 | WAREHOUSE LEVEL\IfcFurnishingElement\2802398__3osoug9Ev0g85atawY75fs\meta.json | Waste Bin Installation | Not Started | The washroom area is unfinished and no waste bin is visible. | Low | The washroom finishes are advancing, but the waste bin is still missing. | Low | The installation area is prepared, but the waste bin is not yet in place. |  | The current scan data is incomplete. | Completed | The waste bin is clearly installed below the wash basin.
3osoug9Ev0g85atawY75he | WB-4/900/T/1000_GROMMETS | IfcFurnishingElement | CK_NHOST_WB-4_OPEN_300:WB-4/900/T/1000_GROMMETS:2802268 | WAREHOUSE LEVEL\IfcFurnishingElement\2802268__3osoug9Ev0g85atawY75he\meta.json | Open Workbench Installation | Low | Only early workbench formation is visible. | Medium | The workbench body is partly installed, but it is not yet fully complete. | High | The workbench is largely in place, with final completion reached later. |  | The current scan data is incomplete. | Completed | The open workbench is installed and reads as complete.
3osoug9Ev0g85atawY75hf | WB-4/900/T/1000_GROMMETS | IfcFurnishingElement | CK_NHOST_WB-4_OPEN_300:WB-4/900/T/1000_GROMMETS:2802267 | WAREHOUSE LEVEL\IfcFurnishingElement\2802267__3osoug9Ev0g85atawY75hf\meta.json | Open Workbench Installation | Low | Only early workbench formation is visible. | Medium | The workbench body is partly installed, but it is not yet fully complete. | High | The workbench is largely in place, with final completion reached later. |  | The current scan data is incomplete. | Completed | The open workbench is installed and reads as complete.
3osoug9Ev0g85atawY75ei | WHC-1/T/1000 | IfcFurnishingElement | CK_WALL_WHC-1_2D_300:WHC-1/T/1000:2802328 | WAREHOUSE LEVEL\IfcFurnishingElement\2802328__3osoug9Ev0g85atawY75ei\meta.json | Wall-Hung Cabinet Installation | Low | The wall zone is prepared, but the cabinet is not yet finished. | Medium | The cabinet body is forming, but final mounting and finish are still incomplete. | High | The cabinet is largely installed, with the finished condition reached later. |  | The current scan data is incomplete. | Completed | The wall-hung cabinet is visibly installed in the finished wall.
3osoug9Ev0g85atawY75eg | WHC-1/T/1000 | IfcFurnishingElement | CK_WALL_WHC-1_2D_300:WHC-1/T/1000:2802330 | WAREHOUSE LEVEL\IfcFurnishingElement\2802330__3osoug9Ev0g85atawY75eg\meta.json | Wall-Hung Cabinet Installation | Low | The wall zone is prepared, but the cabinet is not yet finished. | Medium | The cabinet body is forming, but final mounting and finish are still incomplete. | High | The cabinet is largely installed, with the finished condition reached later. |  | The current scan data is incomplete. | Completed | The wall-hung cabinet is visibly installed in the finished wall.

## IfcRailing
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75eY | PR1_PUBLIC ACESS CORRIDORS/LOBBIES | IfcRailing | 栏杆扶手:PR1_PUBLIC ACESS CORRIDORS/LOBBIES:2802322 | WAREHOUSE LEVEL\IfcRailing\2802322__3osoug9Ev0g85atawY75eY\meta.json | Short Grab Bar Installation | Completed | The short vertical grab bar is already visible at the same wall-edge position and reads as fully installed. | Completed | The short vertical grab bar remains clearly visible at the same position, indicating an installed condition. | Completed | The short vertical grab bar is still present at the same wall-edge position and reads as complete. | Completed | The short vertical grab bar is visible again in the photos and remains in the installed position. | Completed | The short vertical grab bar is present in the finished corridor and remains complete.
3osoug9Ev0g85atawY75ed | PR1_PUBLIC ACESS CORRIDORS/LOBBIES | IfcRailing | 栏杆扶手:PR1_PUBLIC ACESS CORRIDORS/LOBBIES:2802317 | WAREHOUSE LEVEL\IfcRailing\2802317__3osoug9Ev0g85atawY75ed\meta.json | Wall Handrail Installation | Medium | A substantial handrail segment is already in place, but the surrounding wall zone is still under active construction. | High | The handrail run is clearly readable, with only the surrounding finishes still incomplete. | High | The handrail remains largely installed, with final completion confirmed later. |  | The current scan data is incomplete. | Completed | The wall handrail is fully installed in the finished corridor.
3osoug9Ev0g85atawY75kj | PR3C_STAFF ONLY CORRIDORS/ LOBBIES | IfcRailing | 栏杆扶手:PR3C_STAFF ONLY CORRIDORS/ LOBBIES:2802455 | WAREHOUSE LEVEL\IfcRailing\2802455__3osoug9Ev0g85atawY75kj\meta.json | Wall Handrail Installation | High | The handrail run is already clearly mounted, with only minor uncertainty from the unfinished surroundings. | Completed | The handrail appears continuous and fully installed. | Completed | The handrail remains fully installed. | Completed | The handrail remains visible despite partial scan occlusion. | Completed | The handrail is fully installed in the finished corridor.
3osoug9Ev0g85atawY75es | PR3_STAFF ONLY CORRIDORS/ LOBBIES | IfcRailing | 栏杆扶手:PR3_STAFF ONLY CORRIDORS/ LOBBIES:2802334 | WAREHOUSE LEVEL\IfcRailing\2802334__3osoug9Ev0g85atawY75es\meta.json | Wall Handrail Installation | Not Started | Only the wall corner is visible; the handrail itself is not yet evident. | Low | A short segment begins to appear, but the handrail is not substantially installed. | Medium | The handrail zone is formed, but completion is not yet confirmed. |  | The current scan data is incomplete. | Completed | The handrail is present on the finished curved wall.
3osoug9Ev0g85atawY75ep | PR3_STAFF ONLY CORRIDORS/ LOBBIES | IfcRailing | 栏杆扶手:PR3_STAFF ONLY CORRIDORS/ LOBBIES:2802337 | WAREHOUSE LEVEL\IfcRailing\2802337__3osoug9Ev0g85atawY75ep\meta.json | Wall Handrail Installation | Medium | A notable handrail segment is already visible, but the surrounding wall work is unfinished. | Medium | The handrail is partly visible, with later images showing a more complete run. | High | The handrail run is largely continuous along the wall, with final completion seen later. |  | The current scan data is incomplete. | Completed | The wall handrail is clearly installed in the finished corridor.
3osoug9Ev0g85atawY75ew | PR3_STAFF ONLY CORRIDORS/ LOBBIES | IfcRailing | 栏杆扶手:PR3_STAFF ONLY CORRIDORS/ LOBBIES:2802346 | WAREHOUSE LEVEL\IfcRailing\2802346__3osoug9Ev0g85atawY75ew\meta.json | Wall Handrail Installation | High | A long handrail segment is already mounted on the wall, but later scans do not fully confirm final completion. |  | The current scan data is incomplete. |  | The current scan data is incomplete. |  | The current scan data is incomplete. |  | The current scan data is incomplete.

## IfcSlab
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75hl | Generic 25mm | IfcSlab | 楼板:Generic 25mm:2802261 | WAREHOUSE LEVEL\IfcSlab\2802261__3osoug9Ev0g85atawY75hl\meta.json

## IfcWallStandardCase
2025-02-10_Completion
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | local image 是否齐全（没有/一侧/缺失） | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75hw | 基本墙: CORE_GEN | IfcWallStandardCase | 基本墙:CORE_GEN:2802282 | WAREHOUSE LEVEL\IfcWallStandardCase\2802282__3osoug9Ev0g85atawY75hw\meta.json | Drywall installation |  | Low |  | Finished |  | Finished |  | Finished | The previous status was "finished." | Finished
3osoug9Ev0g85atawY75ek | 基本墙: CORE_RADIATION | IfcWallStandardCase | 基本墙:CORE_RADIATION:2802326 | WAREHOUSE LEVEL\IfcWallStandardCase\2802326__3osoug9Ev0g85atawY75ek\meta.json | Drywall installation |  | Medium |  | High |  | Finished |  | Finished | The previous status was "finished." | Finished
3osoug9Ev0g85atawY75el | 基本墙: CORE_RADIATION | IfcWallStandardCase | 基本墙:CORE_RADIATION:2802325 | WAREHOUSE LEVEL\IfcWallStandardCase\2802325__3osoug9Ev0g85atawY75el\meta.json | Drywall installation |  | Medium |  | Uncertain | observed only one side of it. | Uncertain | observed only one side of it. | Uncertain | Missing local image | Finished | the room is already in the decoration phase.
3osoug9Ev0g85atawY75hb | 基本墙: CORE_RADIATION | IfcWallStandardCase | 基本墙:CORE_RADIATION:2802255 | WAREHOUSE LEVEL\IfcWallStandardCase\2802255__3osoug9Ev0g85atawY75hb\meta.json | Drywall installation |  | Medium |  | High |  | High |  | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75hc | 基本墙: CORE_RADIATION | IfcWallStandardCase | 基本墙:CORE_RADIATION:2802254 | WAREHOUSE LEVEL\IfcWallStandardCase\2802254__3osoug9Ev0g85atawY75hc\meta.json | Drywall installation |  | Medium |  | High |  | Finished |  | Finished |  | Finished
3osoug9Ev0g85atawY75eb | 基本墙: FIN_W01 | IfcWallStandardCase | 基本墙:FIN_W01:2802319 | WAREHOUSE LEVEL\IfcWallStandardCase\2802319__3osoug9Ev0g85atawY75eb\meta.json | Painting |  | Not Start |  | Uncertain | observed only one side of it. | High |  | Uncertain (High) | The scope is too narrow. | Finished
3osoug9Ev0g85atawY75hx | 基本墙: FIN_W01 | IfcWallStandardCase | 基本墙:FIN_W01:2802281 | WAREHOUSE LEVEL\IfcWallStandardCase\2802281__3osoug9Ev0g85atawY75hx\meta.json | Painting |  | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain (Medium) | Only one side was observed, yet this side completed the painting. | Uncertain (Medium) | Only one side was observed, yet this side completed the painting. | Finished | the room is already in the decoration phase.
3osoug9Ev0g85atawY75ey | 基本墙: FIN_W01 | IfcWallStandardCase | 基本墙:FIN_W01:2802344 | WAREHOUSE LEVEL\IfcWallStandardCase\2802344__3osoug9Ev0g85atawY75ey\meta.json | Painting |  | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain | Missing local image | Uncertain | Missing local image | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75hY | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802258 | WAREHOUSE LEVEL\IfcWallStandardCase\2802258__3osoug9Ev0g85atawY75hY\meta.json | Painting |  | Not Start | A total of 3 types of input information are considered in the assessment. BIM data outlines the wall's specifications and expected finish. Image evidence clearly shows the wall is absent, with only steel framing visible. Point cloud metrics align with the image findings, reflecting background capture due to the wall's absence. Temporal data is missing. Based on the above, the Stage_label is Painting and Completion is Not Start.", | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Medium |  | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75h4 | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802288 | WAREHOUSE LEVEL\IfcWallStandardCase\2802288__3osoug9Ev0g85atawY75h4\meta.json | Painting |  | Not Start |  | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain (Medium) | Only one side was observed, yet this side completed the painting. | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75eK | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802368 | WAREHOUSE LEVEL\IfcWallStandardCase\2802368__3osoug9Ev0g85atawY75eK\meta.json | Painting |  | Not Start |  | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain (Medium) | Only one side was observed, yet this side completed the painting. | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75h2 | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802290 | WAREHOUSE LEVEL\IfcWallStandardCase\2802290__3osoug9Ev0g85atawY75h2\meta.json | Painting |  | Not Start |  | Uncertain (Not Start) | observed only one side of it. This side hasn't started yet. | Uncertain (Medium) | Only one side was observed, yet this side completed the painting. | Uncertain | Missing local image | Finished
3osoug9Ev0g85atawY75ej | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802327 | WAREHOUSE LEVEL\IfcWallStandardCase\2802327__3osoug9Ev0g85atawY75ej\meta.json | Painting | [9 empty] | Finished
3osoug9Ev0g85atawY75eI | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802370 | WAREHOUSE LEVEL\IfcWallStandardCase\2802370__3osoug9Ev0g85atawY75eI\meta.json | Painting | [9 empty] | Finished
3osoug9Ev0g85atawY75hZ | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802257 | WAREHOUSE LEVEL\IfcWallStandardCase\2802257__3osoug9Ev0g85atawY75hZ\meta.json | Painting | [9 empty] | Finished
3osoug9Ev0g85atawY75h3 | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802289 | WAREHOUSE LEVEL\IfcWallStandardCase\2802289__3osoug9Ev0g85atawY75h3\meta.json | Painting | [9 empty] | Finished
3osoug9Ev0g85atawY75h5 | 基本墙: FIN_W02 | IfcWallStandardCase | 基本墙:FIN_W02:2802287 | WAREHOUSE LEVEL\IfcWallStandardCase\2802287__3osoug9Ev0g85atawY75h5\meta.json | Painting | [9 empty] | Finished

## IfcWindow
IfcGlobalId | Family | IfcType | Name | JSON_RelPath | Stage_label | 10/2/2025_Completion | 10/2/2025_Reason | 17/3/2025_Completion | 17/3/2025_Reason | 11/4/2025_Completion | 11/4/2025_Reason | 2/6/2025_Completion | 2/6/2025_Reason | 1/8/2025_Completion | 1/8/2025_Reason
3osoug9Ev0g85atawY75fp | GLHH-LD | IfcWindow | WW_WALL_ASB_1X1_GZ_1:GLHH-LD:2802401 | WAREHOUSE LEVEL\IfcWindow\2802401__3osoug9Ev0g85atawY75fp\meta.json | Window Installation | Low | This component is a BIM-classified window, with a designed size of approximately 1500 mm by 1250 mm. In the 2025-02-10 site images, the wall opening zone is identifiable, but no completed window frame or glazing system is yet visible; the condition reads as rough opening or very early preparation rather than an installed window. Point cloud analysis reports coverage_grid 16.5%, coverage_hit 17.8%, voxel_recall 13.7%, and voxel_precision 87.5%, which means the detected points are mostly relevant to the target location but cover only a small fraction of the planned window geometry. Therefore, the completion level is assessed as Low. | Medium | By 2025-03-17, the opening is clearly formed and the window zone shows a partial frame or infill condition, but it still does not read as the final glazed assembly observed later. The point cloud metrics improve to coverage_grid 42.5%, coverage_hit 61.0%, voxel_recall 55.9%, and voxel_precision 77.0%, indicating that roughly half of the designed window geometry is now represented in the as-built data. From an engineering point of view, the opening preparation and partial installation are evident, but the system is not yet complete. The completion level is therefore rated Medium. | Medium | On 2025-04-11, the wall around the window is more advanced and the opening remains formed, but the local images still show an unfinished or temporarily infilled appearance rather than the completed glazed window seen at the final date. The point cloud summary gives coverage_grid 28.2%, coverage_hit 48.1%, voxel_recall 39.2%, and voxel_precision 80.0%. Although the numerical overlap is lower than on 2025-03-17, this is consistent with view occlusion and segmentation variation rather than a true regression in site progress. The most defensible engineering judgment is that the window remains at a Medium stage of installation. | High | The 2025-06-02 dataset is incomplete and does not support direct visual or geometric confirmation. The asbuilt_segmented.pcd is empty, processed_mesh_local.ply is missing, and the summary reports coverage_grid 0.0%, coverage_hit 0.0%, voxel_recall 0.0%, and voxel_precision 0.0% because no usable as-built points were written. This is a missing-data issue rather than evidence that the window was absent. Considering that the window is still partial on 2025-04-11 but clearly completed by 2025-08-01, the most reasonable monotonic inference is that by early June the frame and glazing installation were largely advanced. Therefore, this date is rated High, with the note that the judgment is inferred rather than directly observed. | Completed | By 2025-08-01, the room is in a finished condition and the local images show the window frame and glazed panel installed within the completed wall opening. Point cloud analysis reports coverage_grid 58.1%, coverage_hit 75.8%, voxel_recall 67.6%, and voxel_precision 79.3%. These values are below 100% because transparent and reflective glazing is commonly under-captured in point-cloud segmentation, so moderate recall is expected even for a completed window. Combining the geometric evidence with the clear visual confirmation, the window installation is rated Completed.